## Master Checklist
Domain | Control ID | Requirement | Owner | Legal ref(s) | Evidence examples | Frequency | Status (C/IP/R) | Gap severity (H/M/L) | Due date | Notes | Last updated
Governance & BoD | GOV-01 | BoD schvaluje a dohlíží na ICT Risk Management Framework (ICT RMF). | BoD | DORA (governance) – ICT strategy & oversight | Board minutes; Risk appetite statement | Quarterly | C |  |  |  | 2025-12-15
Governance & BoD | GOV-02 | BoD zajišťuje, že ICT strategie je součástí firemní strategie. | BoD | DORA (governance) – ICT strategy & oversight | Board minutes; Risk appetite statement | Quarterly | C | L |  | OK – evidence uploaded (SharePoint /DORA/Governance & BoD). | 2025-12-17
Governance & BoD | GOV-03 | BoD definuje a schvaluje ICT risk appetite & impact tolerances. | BoD | DORA (governance) – ICT strategy & oversight | Risk appetite statement; RACI / roles & responsibilities | Quarterly | IP | M | 2026-05-28 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-15
Governance & BoD | GOV-04 | BoD dostává pravidelné reporty (KRI/KPI) k digitální odolnosti. | CEO | DORA (governance) – ICT strategy & oversight | Board minutes; RACI / roles & responsibilities | Quarterly | C | L |  |  | 2025-12-08
Governance & BoD | GOV-05 | BoD schvaluje rozdělení rolí a pravomocí v ICT oblasti. | CEO | DORA (governance) – ICT strategy & oversight | RACI / roles & responsibilities; Board minutes | Quarterly | C | L |  |  | 2025-12-08
Governance & BoD | GOV-06 | BoD zajišťuje nezávislou kontrolu ICT RMF. | CEO | DORA (governance) – ICT strategy & oversight | Board minutes; RACI / roles & responsibilities | Annual | C |  |  |  | 2025-12-12
Governance & BoD | GOV-07 | BoD je školen v oblasti DORA/NIS2. | CEO | DORA (governance) – ICT strategy & oversight | Board minutes; Risk appetite statement | Quarterly | C | L | 2025-10-17 | OK – evidence uploaded (SharePoint /DORA/Governance & BoD). | 2025-12-14
Governance & BoD | GOV-08 | BoD dohlíží na integraci ICT RMF do ERM (CRO oversight). | Compliance | DORA (governance) – ICT strategy & oversight | Board minutes; ICT strategy | Quarterly | IP | M | 2026-02-24 | Draft exists; finalize policy + approvals. | 2025-12-15
Governance & BoD | GOV-09 | BoD alokuje zdroje (finance, lidi, technologie) pro ICT odolnost. | CEO | DORA (governance) – ICT strategy & oversight | RACI / roles & responsibilities; ICT strategy | Quarterly | IP | M | 2026-02-22 | Process defined; missing evidence from last cycle. | 2025-12-14
Governance & BoD | GOV-10 | BoD schvaluje Digital Operational Resilience Strategy (ročně revidováno). | CEO | DORA (governance) – ICT strategy & oversight | ICT strategy; Board minutes | Annual | C |  |  | OK – evidence uploaded (SharePoint /DORA/Governance & BoD). | 2025-12-10
Governance & BoD | GOV-11 | BoD schvaluje krizový governance rámec. | Compliance | DORA (governance) – ICT strategy & oversight | Risk appetite statement; Board minutes | Quarterly | C | L | 2025-10-18 | OK – evidence uploaded (SharePoint /DORA/Governance & BoD). | 2025-12-07
Governance & BoD | GOV-12 | BoD schvaluje TPRM policy a rozhoduje o strategických dodavatelích. | CEO | DORA (governance) – ICT strategy & oversight | ICT strategy; RACI / roles & responsibilities | Annual | C |  |  | OK – evidence uploaded (SharePoint /DORA/Governance & BoD). | 2025-12-10
Governance & BoD | GOV-13 | BoD schvaluje reporting policy pro regulátory (ČNB/EBA/CSIRT). | Compliance | DORA (governance) – ICT strategy & oversight | Risk appetite statement; ICT strategy | Quarterly | IP | L | 2026-02-08 | Draft exists; finalize policy + approvals. | 2025-12-21
Governance & BoD | GOV-14 | BoD dohlíží, že lessons learned se promítají do strategie. | Compliance | DORA (governance) – ICT strategy & oversight | RACI / roles & responsibilities; Risk appetite statement | Annual | C |  |  |  | 2025-12-17
Governance & BoD | GOV-15 | BoD potvrzuje výroční zprávu o ICT resilience. | Compliance | DORA (governance) – ICT strategy & oversight | ICT strategy; Risk appetite statement | Quarterly | IP | M | 2026-04-07 | Tooling in place; complete procedures + training. | 2025-12-12
ICT RMF | RMF-01 | ICT RMF je zdokumentovaný a schválený BoD. | Head of IT | DORA – ICT risk management framework | Control testing evidence; KRI dashboard export | Monthly | IP | L | 2026-03-18 | Tooling in place; complete procedures + training. | 2025-12-13
ICT RMF | RMF-02 | ICT RMF je integrován do ERM (poznámka: CRO vlastní ERM). | CISO | DORA – ICT risk management framework | KRI dashboard export; Control testing evidence | Monthly | C | L |  |  | 2025-12-17
ICT RMF | RMF-03 | ICT RMF je revidován min. 1× ročně. | IT Risk | DORA – ICT risk management framework | ICT RMF policy; Control testing evidence | Monthly | IP | M | 2026-03-19 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-16
ICT RMF | RMF-04 | ICT RMF pokrývá všechny kritické/important business functions (CIFs) a systémy. | CISO | DORA – ICT risk management framework | ICT RMF policy; Control testing evidence | Quarterly | IP | M | 2026-06-05 | Tooling in place; complete procedures + training. | 2025-12-15
ICT RMF | RMF-05 | Uplatněn princip proporcionality adekvátně k velikosti/složitosti. | IT Risk | DORA – ICT risk management framework | Control testing evidence; ICT RMF policy | Quarterly | C |  |  |  | 2025-12-19
ICT RMF | RMF-06 | Inventář ICT aktiv (HW, SW, data, služby, cloud) je kompletní. | CISO | DORA – ICT risk management framework | Risk register; ICT RMF policy | Quarterly | IP | M | 2026-05-20 | Process defined; missing evidence from last cycle. | 2025-12-11
ICT RMF | RMF-07 | Business impact analýza (BIA) identifikuje CIFs. | CISO | DORA – ICT risk management framework | Risk register; KRI dashboard export | Monthly | IP | M | 2026-05-07 | Draft exists; finalize policy + approvals. | 2025-12-21
ICT RMF | RMF-08 | Evidované ICT závislosti (včetně třetích stran) jsou aktuální. | IT Risk | DORA – ICT risk management framework | Risk register; KRI dashboard export | Monthly | C |  |  | OK – evidence uploaded (SharePoint /DORA/ICT RMF). | 2025-12-09
ICT RMF | RMF-09 | Data/informace jsou klasifikována dle citlivosti a kritičnosti. | CISO | DORA – ICT risk management framework | Risk register; ICT RMF policy | Monthly | C | L |  | OK – evidence uploaded (SharePoint /DORA/ICT RMF). | 2025-12-07
ICT RMF | RMF-10 | Pro klíčová aktiva jsou určeni vlastníci (asset owners). | Head of IT | DORA – ICT risk management framework | ICT RMF policy; Risk register | Quarterly | C |  |  | OK – evidence uploaded (SharePoint /DORA/ICT RMF). | 2025-12-11
ICT RMF | RMF-11 | ICT risk assessment probíhá min. 1× ročně a při významných změnách. | Head of IT | DORA – ICT risk management framework | ICT RMF policy; Control testing evidence | Monthly | IP | M | 2026-02-09 | Process defined; missing evidence from last cycle. | 2025-12-21
ICT RMF | RMF-12 | Risk assessment zahrnuje hrozby, zranitelnosti, dopady a pravděpodobnosti. | IT Risk | DORA – ICT risk management framework | ICT RMF policy; KRI dashboard export | Monthly | IP | M | 2026-06-10 | Process defined; missing evidence from last cycle. | 2025-12-14
ICT RMF | RMF-13 | Výsledky risk assessmentů jsou reportovány BoD a zohledněny ve strategii. | Head of IT | DORA – ICT risk management framework | Control testing evidence; KRI dashboard export | Monthly | R | H | 2025-12-24 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-23
ICT RMF | RMF-14 | Používá se standardizovaná metodika a škály rizik. | Head of IT | DORA – ICT risk management framework | ICT RMF policy; Risk register | Quarterly | IP | M | 2026-03-28 | Process defined; missing evidence from last cycle. | 2025-12-19
ICT RMF | RMF-15 | Rizika mají vlastníky, mitigace a termíny; je veden plán nápravných opatření. | CISO | DORA – ICT risk management framework | Control testing evidence; ICT RMF policy | Monthly | IP | L | 2026-03-31 | Tooling in place; complete procedures + training. | 2025-12-20
ICT RMF | RMF-16 | Bezpečnostní politika stanovuje minimální standardy (MFA, hardening, konfigurace). | CISO | DORA – ICT risk management framework | Risk register; Control testing evidence | Quarterly | IP | M | 2026-03-06 | Draft exists; finalize policy + approvals. | 2025-12-11
ICT RMF | RMF-17 | Patching a bezpečnostní aktualizace jsou řízeny SLA a evidencí výjimek. | IT Risk | DORA – ICT risk management framework | KRI dashboard export; ICT RMF policy | Monthly | R | H | 2026-04-06 | No formal documentation; implement minimum controls immediately. | 2025-12-16
ICT RMF | RMF-18 | Přístupy jsou řízeny principem least privilege; pravidelné recertyfikace. | CISO | DORA – ICT risk management framework | Control testing evidence; Risk register | Quarterly | R | H | 2026-03-13 | High risk. Vendor/tool selection required; budget approval pending. | 2025-12-23
ICT RMF | RMF-19 | Segmentace sítě odděluje kritické systémy a snižuje laterální pohyb. | IT Risk | DORA – ICT risk management framework | KRI dashboard export; Risk register | Quarterly | IP | M | 2026-01-27 | Tooling in place; complete procedures + training. | 2025-12-14
ICT RMF | RMF-20 | Ochrana proti malware/phishingu je implementována a řízena (AV/EDR/anti‑phishing). | IT Risk | DORA – ICT risk management framework | KRI dashboard export; Risk register | Quarterly | C |  | 2025-10-17 |  | 2025-12-15
ICT RMF | RMF-21 | SIEM/SOC je implementován pro monitoring a korelaci událostí. | CISO | DORA – ICT risk management framework | KRI dashboard export; ICT RMF policy | Quarterly | C | L |  |  | 2025-12-06
ICT RMF | RMF-22 | Definované detekční use‑cases a alerty jsou aktivně udržovány (tuning). | IT Risk | DORA – ICT risk management framework | Risk register; KRI dashboard export | Monthly | IP | M | 2026-05-03 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-20
ICT RMF | RMF-23 | Log management pokrývá klíčové systémy; definovaná retence a integrita logů. | CISO | DORA – ICT risk management framework | KRI dashboard export; ICT RMF policy | Monthly | C | L | 2025-10-16 | OK – evidence uploaded (SharePoint /DORA/ICT RMF). | 2025-12-15
ICT RMF | RMF-24 | On‑call/SOC má definované reakční časy a eskalační postupy. | CISO | DORA – ICT risk management framework | Control testing evidence; ICT RMF policy | Quarterly | IP | M | 2026-02-16 | Draft exists; finalize policy + approvals. | 2025-12-13
ICT RMF | RMF-25 | Incidenty a anomálie jsou klasifikovány a eskalovány dle procesu. | IT Risk | DORA – ICT risk management framework | ICT RMF policy; Risk register | Monthly | R | M | 2026-04-12 | No formal documentation; implement minimum controls immediately. | 2025-12-22
Business Continuity | BCM-01 | BCM politika existuje a je schválena. | Head of IT | DORA – ICT business continuity & resilience | BC test results; Crisis playbook | Annual | C | L |  | OK – evidence uploaded (SharePoint /DORA/Business Continuity). | 2025-12-11
Business Continuity | BCM-02 | BCP pokrývají všechny kritické funkce a ICT systémy. | COO | DORA – ICT business continuity & resilience | BC test results; BCP/DR plan | Semi‑annual | IP | M | 2026-02-17 | Draft exists; finalize policy + approvals. | 2025-12-14
Business Continuity | BCM-03 | DR plány jsou vytvořeny pro klíčové systémy. | COO | DORA – ICT business continuity & resilience | BCP/DR plan; BC test results | Annual | IP | M | 2026-02-18 | Tooling in place; complete procedures + training. | 2025-12-21
Business Continuity | BCM-04 | Každý plán má definované RTO a RPO. | COO | DORA – ICT business continuity & resilience | RTO/RPO list; Crisis playbook | Annual | R | M | 2026-03-01 | Not implemented. Start remediation project; define owner & roadmap. | 2025-12-20
Business Continuity | BCM-05 | BCP/DR jsou v souladu s DORA/NIS2 požadavky. | BCM | DORA – ICT business continuity & resilience | Crisis playbook; RTO/RPO list | Annual | IP | M | 2026-01-27 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-12
Business Continuity | BCM-06 | BCP/DR se testují minimálně 1× ročně. | COO | DORA – ICT business continuity & resilience | BC test results; BCP/DR plan | Semi‑annual | IP | L | 2026-03-20 | Tooling in place; complete procedures + training. | 2025-12-13
Business Continuity | BCM-07 | Testy zahrnují vícero scénářů (ICT výpadek, kyber, dodavatel apod.). | Head of IT | DORA – ICT business continuity & resilience | BCP/DR plan; RTO/RPO list | Annual | R | M | 2026-03-01 | High risk. Vendor/tool selection required; budget approval pending. | 2025-12-16
Business Continuity | BCM-08 | Evidence výsledků testů je dokumentována včetně vyhodnocení. | BCM | DORA – ICT business continuity & resilience | Crisis playbook; BCP/DR plan | Semi‑annual | C | L |  |  | 2025-12-12
Business Continuity | BCM-09 | Lessons learned z testů jsou promítnuty do plánů a kontrol. | BCM | DORA – ICT business continuity & resilience | BCP/DR plan; BC test results | Annual | IP | M | 2026-01-27 | Draft exists; finalize policy + approvals. | 2025-12-14
Business Continuity | BCM-10 | Testy zahrnují krizovou komunikaci. | BCM | DORA – ICT business continuity & resilience | RTO/RPO list; Crisis playbook | Annual | C | L |  |  | 2025-12-19
Business Continuity | BCM-11 | Krizový tým je jmenován s rolemi a kontakty. | BCM | DORA – ICT business continuity & resilience | BC test results; RTO/RPO list | Semi‑annual | IP | M | 2026-04-11 | Draft exists; finalize policy + approvals. | 2025-12-19
Business Continuity | BCM-12 | Připravené šablony krizové komunikace pro zaměstnance/klienty/regulátory. | COO | DORA – ICT business continuity & resilience | BC test results; BCP/DR plan | Annual | IP | L | 2026-02-15 | Tooling in place; complete procedures + training. | 2025-12-19
Business Continuity | BCM-13 | Definovaný proces eskalace během krize. | Head of IT | DORA – ICT business continuity & resilience | BCP/DR plan; RTO/RPO list | Semi‑annual | C | L | 2025-10-19 | OK – evidence uploaded (SharePoint /DORA/Business Continuity). | 2025-12-11
Business Continuity | BCM-14 | Zálohovací politika definuje rozsah, frekvenci a úložiště (vč. immutable). | Head of IT | DORA – ICT business continuity & resilience | BCP/DR plan; BC test results | Semi‑annual | C |  |  |  | 2025-12-17
Business Continuity | BCM-15 | Obnova ze záloh se pravidelně testuje a eviduje. | Head of IT | DORA – ICT business continuity & resilience | RTO/RPO list; BCP/DR plan | Semi‑annual | R | M | 2026-04-09 | Not implemented. Start remediation project; define owner & roadmap. | 2025-12-19
Incident Mgmt & Reporting | INC-01 | Incident Response Plan je schválen a aktuální. | Compliance | DORA – incident management & reporting | Incident policy; Major incident runbook | Quarterly | IP | L | 2026-03-16 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-16
Incident Mgmt & Reporting | INC-02 | Incidenty jsou kategorizovány (major / non‑major) dle kritérií. | SOC Lead | DORA – incident management & reporting | Major incident runbook; Regulator notification log | Continuous | R | H | 2026-02-11 | No formal documentation; implement minimum controls immediately. | 2025-12-20
Incident Mgmt & Reporting | INC-03 | Klasifikace pokrývá CIA, reputaci a compliance dopady. | SOC Lead | DORA – incident management & reporting | Post‑mortems; Regulator notification log | Continuous | C | L |  |  | 2025-12-13
Incident Mgmt & Reporting | INC-04 | SLA reakce (P1‑P3) jsou definovány a sledovány. | Compliance | DORA – incident management & reporting | Incident policy; Regulator notification log | Continuous | IP | M | 2026-02-16 | Assign RACI; run pilot and capture evidence. | 2025-12-12
Incident Mgmt & Reporting | INC-05 | Role a odpovědnosti v IM jsou definovány (IM, technika, komunikace). | SOC Lead | DORA – incident management & reporting | Regulator notification log; Major incident runbook | Quarterly | R | H | 2026-01-23 | No formal documentation; implement minimum controls immediately. | 2025-12-20
Incident Mgmt & Reporting | INC-06 | Playbooky existují (ransomware, phishing, DDoS, data breach, cloud outage). | CISO | DORA – incident management & reporting | Post‑mortems; Incident policy | Continuous | IP | M | 2026-06-09 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-21
Incident Mgmt & Reporting | INC-07 | Evidence incidentů v ITSM; jednotné číslování. | Compliance | DORA – incident management & reporting | Incident policy; Major incident runbook | Continuous | IP | M | 2026-02-17 | Tooling in place; complete procedures + training. | 2025-12-15
Incident Mgmt & Reporting | INC-08 | Post‑incident review povinné pro každý major incident. | CISO | DORA – incident management & reporting | Post‑mortems; Major incident runbook | Quarterly | IP | M | 2026-06-14 | Tooling in place; complete procedures + training. | 2025-12-22
Incident Mgmt & Reporting | INC-09 | Trend analýza incidentů reportována BoD. | SOC Lead | DORA – incident management & reporting | Regulator notification log; Post‑mortems | Continuous | IP | L | 2026-04-29 | Assign RACI; run pilot and capture evidence. | 2025-12-21
Incident Mgmt & Reporting | INC-10 | Incident management je provázán s BCP/DR. | CISO | DORA – incident management & reporting | Major incident runbook; Incident policy | Continuous | IP | M | 2026-04-14 | Assign RACI; run pilot and capture evidence. | 2025-12-17
Incident Mgmt & Reporting | INC-11 | DORA: initial notification ≤4 h od klasifikace a ≤24 h od detekce. | CISO | DORA – incident management & reporting | Post‑mortems; Regulator notification log | Continuous | IP | M | 2026-05-20 | Draft exists; finalize policy + approvals. | 2025-12-13
Incident Mgmt & Reporting | INC-12 | DORA: intermediate report ≤72 h. | SOC Lead | DORA – incident management & reporting | Regulator notification log; Incident policy | Continuous | IP | M | 2026-02-18 | Draft exists; finalize policy + approvals. | 2025-12-17
Incident Mgmt & Reporting | INC-13 | DORA: final report ≤1 měsíc (root cause + mitigace). | Compliance | DORA – incident management & reporting | Regulator notification log; Major incident runbook | Quarterly | IP | M | 2026-02-02 | Tooling in place; complete procedures + training. | 2025-12-18
Incident Mgmt & Reporting | INC-14 | DORA: používají se EU šablony a kanály pro reporting. | Compliance | DORA – incident management & reporting | Regulator notification log; Incident policy | Continuous | C | L |  | OK – evidence uploaded (SharePoint /DORA/Incident Mgmt & Reporting). | 2025-12-11
Incident Mgmt & Reporting | INC-15 | DORA: proces pro agregovaný reporting (multi‑entity) je definován. | Compliance | DORA – incident management & reporting | Post‑mortems; Regulator notification log | Continuous | IP | M | 2026-03-11 | Tooling in place; complete procedures + training. | 2025-12-21
Incident Mgmt & Reporting | INC-16 | DORA: audit trail všech odeslaných reportů je archivován. | CISO | DORA – incident management & reporting | Major incident runbook; Post‑mortems | Quarterly | R | H | 2026-03-21 | High risk. Vendor/tool selection required; budget approval pending. | 2025-12-16
Incident Mgmt & Reporting | INC-17 | NIS2: early warning ≤24 h od zjištění významného incidentu. | Compliance | DORA – incident management & reporting | Major incident runbook; Post‑mortems | Continuous | R | H | 2026-02-28 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-17
Incident Mgmt & Reporting | INC-18 | NIS2: incident notification ≤72 h s počáteční analýzou a IOCs. | CISO | DORA – incident management & reporting | Major incident runbook; Post‑mortems | Quarterly | R | H | 2025-12-25 | Not implemented. Start remediation project; define owner & roadmap. | 2025-12-22
Incident Mgmt & Reporting | INC-19 | NIS2: final report ≤1 měsíc / průběžné zprávy dle potřeby. | SOC Lead | DORA – incident management & reporting | Incident policy; Regulator notification log | Continuous | IP | M | 2026-05-09 | Process defined; missing evidence from last cycle. | 2025-12-12
Incident Mgmt & Reporting | INC-20 | Komunikační matice pro incidenty (interní, klienti, média, regulátor). | Compliance | DORA – incident management & reporting | Post‑mortems; Regulator notification log | Quarterly | IP | L | 2026-05-02 | Assign RACI; run pilot and capture evidence. | 2025-12-12
Incident Mgmt & Reporting | INC-21 | Šablony externí komunikace připraveny a schváleny. | Compliance | DORA – incident management & reporting | Regulator notification log; Incident policy | Quarterly | R | H | 2025-12-29 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-16
Incident Mgmt & Reporting | INC-22 | Odpovědnost za formální komunikaci s regulátory definována (Legal support). | SOC Lead | DORA – incident management & reporting | Post‑mortems; Incident policy | Quarterly | IP | L | 2026-03-08 | Process defined; missing evidence from last cycle. | 2025-12-19
Incident Mgmt & Reporting | INC-23 | Simulace major incidentů včetně reportingových lhůt probíhají. | Compliance | DORA – incident management & reporting | Regulator notification log; Post‑mortems | Continuous | R | M | 2026-02-26 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-21
Testing | TST-01 | Program testování digitální odolnosti schválen. | Security | DORA – testing (TLPT/regular testing) | Patch compliance report; Test plan & schedule | Monthly | IP | M | 2026-04-09 | Assign RACI; run pilot and capture evidence. | 2025-12-22
Testing | TST-02 | Program je risk‑based s prioritizací scénářů. | CISO | DORA – testing (TLPT/regular testing) | Patch compliance report; Pen test report | Monthly | IP | L | 2026-04-14 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-11
Testing | TST-03 | Zahrnuty typy testů: VA, PEN, výkon, DR, tabletop. | Test Lead | DORA – testing (TLPT/regular testing) | Patch compliance report; Test plan & schedule | Monthly | C | L |  | OK – evidence uploaded (SharePoint /DORA/Testing). | 2025-12-13
Testing | TST-04 | Evidence/test plány a zprávy jsou archivovány. | Test Lead | DORA – testing (TLPT/regular testing) | Vulnerability scans; Patch compliance report | Quarterly | C | L |  |  | 2025-12-06
Testing | TST-05 | Role a odpovědnosti testování (interní/externí) definovány. | CISO | DORA – testing (TLPT/regular testing) | Vulnerability scans; Pen test report | Quarterly | IP | M | 2026-06-15 | Assign RACI; run pilot and capture evidence. | 2025-12-11
Testing | TST-06 | TLPT povinnost posouzena dle RTS; záznam o rozhodnutí. | Test Lead | DORA – testing (TLPT/regular testing) | Patch compliance report; Pen test report | Monthly | R | M | 2026-04-02 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-16
Testing | TST-07 | TLPT scope schválen (systémy, scénáře, threat intel). | CISO | DORA – testing (TLPT/regular testing) | Test plan & schedule; Patch compliance report | Quarterly | IP | M | 2026-06-18 | Draft exists; finalize policy + approvals. | 2025-12-22
Testing | TST-08 | TLPT provider je nezávislý a kvalifikovaný. | CISO | DORA – testing (TLPT/regular testing) | Test plan & schedule; Patch compliance report | Monthly | IP | M | 2026-02-15 | Process defined; missing evidence from last cycle. | 2025-12-11
Testing | TST-09 | Závěrečná zpráva TLPT + CAPA uzavřena. | Test Lead | DORA – testing (TLPT/regular testing) | Vulnerability scans; Test plan & schedule | Quarterly | R | H | 2026-03-24 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-21
Testing | TST-10 | Lessons learned z testů implementovány do ICT RMF. | Test Lead | DORA – testing (TLPT/regular testing) | Test plan & schedule; Patch compliance report | Monthly | IP | M | 2026-05-15 | Tooling in place; complete procedures + training. | 2025-12-13
TPRM | TPR-01 | TPRM strategie existuje a je schválena. | Procurement | DORA – ICT third‑party risk management | SOC2/ISO certs; Contract clauses | Quarterly | IP | L | 2026-05-11 | Draft exists; finalize policy + approvals. | 2025-12-11
TPRM | TPR-02 | TPRM politika ICT třetích stran je schválena BoD. | Risk | DORA – ICT third‑party risk management | Exit plan; Contract clauses | Annual | R | H | 2026-02-06 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-16
TPRM | TPR-03 | Politika pokrývá CIFs a diferencuje režimy dle kritičnosti. | Procurement | DORA – ICT third‑party risk management | SOC2/ISO certs; Exit plan | Quarterly | IP | M | 2026-04-25 | Tooling in place; complete procedures + training. | 2025-12-17
TPRM | TPR-04 | Proporcionalita u TPRM aplikována (tiering dodavatelů). | Procurement | DORA – ICT third‑party risk management | Contract clauses; Exit plan | Quarterly | IP | M | 2026-04-01 | Draft exists; finalize policy + approvals. | 2025-12-17
TPRM | TPR-05 | Předkontraktní due diligence je povinná pro všechny ICT dodavatele. | Procurement | DORA – ICT third‑party risk management | Contract clauses; Exit plan | Quarterly | C | L |  | OK – evidence uploaded (SharePoint /DORA/TPRM). | 2025-12-07
TPRM | TPR-06 | Due diligence zahrnuje finanční, bezpečnostní, geografické, reputační faktory. | Legal | DORA – ICT third‑party risk management | Due diligence checklist; SOC2/ISO certs | Quarterly | R | M | 2026-04-03 | Not implemented. Start remediation project; define owner & roadmap. | 2025-12-21
TPRM | TPR-07 | Koncentrační riziko je vyhodnoceno (včetně cloudových hyperscalerů). | Risk | DORA – ICT third‑party risk management | Exit plan; Contract clauses | Annual | IP | M | 2026-05-23 | Draft exists; finalize policy + approvals. | 2025-12-20
TPRM | TPR-08 | Existuje exit/transition plán pro kritické služby. | Legal | DORA – ICT third‑party risk management | Exit plan; Due diligence checklist | Annual | IP | L | 2026-04-25 | Process defined; missing evidence from last cycle. | 2025-12-15
TPRM | TPR-09 | Smlouvy obsahují audit rights/inspekci a přístup k logům/datům. | Procurement | DORA – ICT third‑party risk management | Exit plan; Due diligence checklist | Annual | IP | M | 2026-04-06 | Process defined; missing evidence from last cycle. | 2025-12-17
TPRM | TPR-10 | Smlouvy specifikují data/location požadavky a schvalování subdodavatelů. | Procurement | DORA – ICT third‑party risk management | Contract clauses; Exit plan | Annual | IP | L | 2026-06-06 | Process defined; missing evidence from last cycle. | 2025-12-21
TPRM | TPR-11 | Smlouvy mají jasná SLA/KPI a sankční mechanismy. | Procurement | DORA – ICT third‑party risk management | Contract clauses; Due diligence checklist | Quarterly | IP | M | 2026-06-25 | Tooling in place; complete procedures + training. | 2025-12-22
TPRM | TPR-12 | Smlouvy u CIF vyžadují BCP/DR povinnosti dodavatele a testy. | Legal | DORA – ICT third‑party risk management | SOC2/ISO certs; Due diligence checklist | Quarterly | IP | L | 2026-04-20 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-17
TPRM | TPR-13 | Centrální registr ICT třetích stran je veden (provider, služba, CIF, lokace). | Procurement | DORA – ICT third‑party risk management | Due diligence checklist; Exit plan | Annual | IP | M | 2026-03-08 | Assign RACI; run pilot and capture evidence. | 2025-12-19
TPRM | TPR-14 | Registr zahrnuje subdodavatele a tok dat. | Procurement | DORA – ICT third‑party risk management | Contract clauses; SOC2/ISO certs | Annual | IP | M | 2026-05-28 | Process defined; missing evidence from last cycle. | 2025-12-11
TPRM | TPR-15 | Registr je aktualizován min. 1× ročně a po změnách. | Legal | DORA – ICT third‑party risk management | SOC2/ISO certs; Due diligence checklist | Quarterly | R | M | 2026-04-19 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-21
TPRM | TPR-16 | Ongoing monitoring dodavatelů – KPI/KRI a review meetingy. | Risk | DORA – ICT third‑party risk management | Due diligence checklist; SOC2/ISO certs | Annual | R | M | 2026-03-25 | No formal documentation; implement minimum controls immediately. | 2025-12-17
TPRM | TPR-17 | Dodavatelé poskytují nezávislé assurance (ISO 27001, SOC 2, ISAE 3402). | Procurement | DORA – ICT third‑party risk management | Contract clauses; Due diligence checklist | Annual | R | H | 2026-01-01 | High risk. Vendor/tool selection required; budget approval pending. | 2025-12-19
TPRM | TPR-18 | Proces pro incidenty dodavatele je definován a provázán na vlastní IM. | Legal | DORA – ICT third‑party risk management | Contract clauses; Due diligence checklist | Annual | R | H | 2026-01-13 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-19
TPRM | TPR-19 | Audit rights byly uplatněny alespoň na vzorku kritických dodavatelů. | Risk | DORA – ICT third‑party risk management | Contract clauses; SOC2/ISO certs | Quarterly | IP | M | 2026-06-10 | Draft exists; finalize policy + approvals. | 2025-12-21
TPRM | TPR-20 | Výsledky TPRM oversightu reportovány BoD. | Legal | DORA – ICT third‑party risk management | Contract clauses; Exit plan | Annual | IP | M | 2026-05-04 | Process defined; missing evidence from last cycle. | 2025-12-21
Information Sharing | INF-01 | Strategie zapojení do threat‑intel komunit definována. | Compliance | DORA – information sharing | Sharing procedure; ISAC participation proof | Quarterly | IP | M | 2026-01-11 | Draft exists; finalize policy + approvals. | 2025-12-21
Information Sharing | INF-02 | Aktivní členství v relevantních TI platformách (FS‑ISAC, CSIRT). | Risk | DORA – information sharing | Sharing procedure; Threat intel feed logs | Monthly | IP | M | 2026-02-23 | Process defined; missing evidence from last cycle. | 2025-12-12
Information Sharing | INF-03 | Interní pravidla co/ jak sdílet (IOCs, TTPs) existují. | Compliance | DORA – information sharing | ISAC participation proof; Threat intel feed logs | Quarterly | IP | L | 2026-01-16 | Draft exists; finalize policy + approvals. | 2025-12-16
Information Sharing | INF-04 | Postupy anonymizace/sanitizace dat před sdílením jsou definovány. | CISO | DORA – information sharing | ISAC participation proof; Sharing procedure | Monthly | R | H | 2026-01-02 | High risk. Vendor/tool selection required; budget approval pending. | 2025-12-21
Information Sharing | INF-05 | Evidence TI sdílení/čerpaní je vedena a auditovatelná. | Compliance | DORA – information sharing | Threat intel feed logs; ISAC participation proof | Monthly | C | L |  | OK – evidence uploaded (SharePoint /DORA/Information Sharing). | 2025-12-09
Information Sharing | INF-06 | Výstupy TI jsou integrovány do SOC/monitoringu a IRP. | CISO | DORA – information sharing | Sharing procedure; Threat intel feed logs | Quarterly | C | L |  |  | 2025-12-12
NIS2 Obligations | NIS2-01 | BoD schválil opatření pro řízení kybernetických rizik dle NIS2. | Compliance | NIS2 – risk measures & incident reporting | Incident reporting procedure; Training records | Quarterly | IP | L | 2026-04-12 | Assign RACI; run pilot and capture evidence. | 2025-12-18
NIS2 Obligations | NIS2-02 | BoD zajistil školení top managementu o povinnostech NIS2. | Legal | NIS2 – risk measures & incident reporting | Incident reporting procedure; NIS2 GAP assessment | Annual | R | H | 2026-04-22 | High risk. Vendor/tool selection required; budget approval pending. | 2025-12-19
NIS2 Obligations | NIS2-03 | Politika risk analysis a bezpečnosti IS existuje a je aktuální. | CISO | NIS2 – risk measures & incident reporting | Incident reporting procedure; Security policy set | Quarterly | IP | L | 2026-03-11 | Assign RACI; run pilot and capture evidence. | 2025-12-21
NIS2 Obligations | NIS2-04 | Incident handling capability (detekce‑reakce‑obnova) je funkční. | Legal | NIS2 – risk measures & incident reporting | Incident reporting procedure; NIS2 GAP assessment | Quarterly | R | H | 2026-01-29 | Major gap. Missing process + evidence; prioritize in Q1. | 2025-12-22
NIS2 Obligations | NIS2-05 | Business continuity & crisis management včetně záloh/DR je implementován. | CISO | NIS2 – risk measures & incident reporting | Security policy set; Training records | Annual | IP | L | 2026-02-25 | Assign RACI; run pilot and capture evidence. | 2025-12-15
NIS2 Obligations | NIS2-06 | Supply‑chain security je integrována do nákupů a kontraktů. | Compliance | NIS2 – risk measures & incident reporting | Training records; Security policy set | Annual | IP | M | 2026-03-08 | Tooling in place; complete procedures + training. | 2025-12-11
NIS2 Obligations | NIS2-07 | Secure SDLC je zaveden pro akvizici/vývoj/údržbu systémů. | Compliance | NIS2 – risk measures & incident reporting | Incident reporting procedure; NIS2 GAP assessment | Quarterly | C | L |  |  | 2025-12-16
NIS2 Obligations | NIS2-08 | Efektivita opatření je pravidelně hodnocena (audity/maturity). | Legal | NIS2 – risk measures & incident reporting | NIS2 GAP assessment; Security policy set | Quarterly | IP | L | 2026-03-16 | Tooling in place; complete procedures + training. | 2025-12-18
NIS2 Obligations | NIS2-09 | Školení kyber hygieny probíhá a je dokumentováno. | CISO | NIS2 – risk measures & incident reporting | Security policy set; Training records | Quarterly | IP | L | 2026-05-29 | Assign RACI; run pilot and capture evidence. | 2025-12-19
NIS2 Obligations | NIS2-10 | HR security, access control a asset management politiky jsou v praxi. | Compliance | NIS2 – risk measures & incident reporting | NIS2 GAP assessment; Incident reporting procedure | Annual | IP | L | 2026-01-17 | Draft exists; finalize policy + approvals. | 2025-12-20
NIS2 Obligations | NIS2-11 | MFA/konzistentní autentizace je nasazena na všech systémech. | Legal | NIS2 – risk measures & incident reporting | Security policy set; NIS2 GAP assessment | Quarterly | C | L |  |  | 2025-12-15
NIS2 Obligations | NIS2-12 | Šifrovaná komunikace a key management jsou zavedeny. | Compliance | NIS2 – risk measures & incident reporting | Security policy set; NIS2 GAP assessment | Annual | IP | M | 2026-04-26 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-18
NIS2 Obligations | NIS2-13 | Early warning do 24 h směrem k CSIRT/autor. je zajištěn. | CISO | NIS2 – risk measures & incident reporting | Incident reporting procedure; Training records | Annual | IP | M | 2026-02-17 | Process defined; missing evidence from last cycle. | 2025-12-11
NIS2 Obligations | NIS2-14 | Incident notification do 72 h včetně IOCs je procesně zajištěn. | Legal | NIS2 – risk measures & incident reporting | Incident reporting procedure; Training records | Quarterly | IP | L | 2026-01-13 | Assign RACI; run pilot and capture evidence. | 2025-12-21
NIS2 Obligations | NIS2-15 | Final report do 1 měsíce (nebo průběžné) je dodržován. | CISO | NIS2 – risk measures & incident reporting | Security policy set; Training records | Quarterly | IP | L | 2026-03-17 | Assign RACI; run pilot and capture evidence. | 2025-12-17
EBA Guidelines | EBA-01 | Mapping EBA GL vs. DORA je zdokumentován (scope & overlap). | Internal Audit | EBA – outsourcing & ICT/security guidelines | Outsourcing register; EBA compliance mapping | Annual | C |  |  | OK – evidence uploaded (SharePoint /DORA/EBA Guidelines). | 2025-12-19
EBA Guidelines | EBA-02 | Reziduální PSD2/EBA povinnosti jsou identifikovány a vlastníky určeny. | Compliance | EBA – outsourcing & ICT/security guidelines | Materiality assessment; Outsourcing register | Annual | C |  |  |  | 2025-12-07
EBA Guidelines | EBA-03 | Důkazy o pokrytí EBA GL DORA nebo zachování povinností jsou k dispozici. | Compliance | EBA – outsourcing & ICT/security guidelines | Outsourcing register; Materiality assessment | Quarterly | C | L |  |  | 2025-12-15
EBA Guidelines | EBA-04 | Outsourcing policy sladěna s DORA i EBA GL. | Compliance | EBA – outsourcing & ICT/security guidelines | Outsourcing register; Materiality assessment | Quarterly | IP | M | 2026-01-15 | Tooling in place; complete procedures + training. | 2025-12-11
EBA Guidelines | EBA-05 | Outsourcing register splňuje EBA požadavky (funkce, data, lokace, exit). | Internal Audit | EBA – outsourcing & ICT/security guidelines | Outsourcing register; Materiality assessment | Quarterly | IP | M | 2026-05-19 | Align with DORA template; add KRIs & reporting cadence. | 2025-12-19
EBA Guidelines | EBA-06 | Outsourcing smlouvy obsahují povinné EBA klauzule (audit/access/location/subcontracting/exit). | Internal Audit | EBA – outsourcing & ICT/security guidelines | EBA compliance mapping; Outsourcing register | Quarterly | IP | L | 2026-05-30 | Tooling in place; complete procedures + training. | 2025-12-16
EBA Guidelines | EBA-07 | Pravidelný review policy a registru vůči EBA doporučením probíhá. | Risk | EBA – outsourcing & ICT/security guidelines | Outsourcing register; EBA compliance mapping | Quarterly | IP | M | 2026-03-12 | Tooling in place; complete procedures + training. | 2025-12-22

## TPRM Register
Provider name | Service / System | Critical/Important Function (Y/N) | Business owner | Data categories (PII/Payment/Other) | Data residency/locations | Regulated data involved (Y/N) | Subcontractors (known) | Concentration risk notes | Reliance level (users/functions impacted) | Onboarding due diligence (Y/N) | Contract signed date | Key clauses present (audit/access/termination/MFA/etc.) | Assurance provided (ISO/SOC) | Monitoring KPIs/KRIs | Exit/transition plan (Y/N) | Next review date | Notes
Microsoft | Microsoft 365 (Email/Collab) | Y | IT | PII/Other | EU (Dublin/Amsterdam) | Y | n/a | High concentration | High | Y | 2024-06-01 | audit; access; termination; MFA | ISO 27001 | Availability; incidents | Y | 2026-03-31 | Annual review; verify subprocessor list
Amazon | AWS (Hosting) | Y | IT | PII/Other | EU (Frankfurt) | Y | n/a | Vendor lock‑in | High | Y | 2024-02-15 | audit; access; termination; encryption | SOC 2 Type II | Uptime; DR tests | Y | 2026-02-28 | Exit plan draft needed
Cloudflare | CDN / WAF | N | IT | Other | EU | N | n/a |  | Medium | Y | 2025-01-10 | audit; security addendum | SOC 2 | WAF alerts; latency | N | 2026-01-31 | Add exit/transition procedure
Vercel | App hosting | Y | IT | PII/Other | EU/US (multi‑region) | Y | n/a | US processing risk | Medium | Y | 2025-09-01 | audit; termination; incident notice | SOC 2 | Deploy success; downtime | N | 2026-06-30 | Confirm EU region settings
Supabase | Database & Auth | Y | IT | PII | EU | Y | n/a | Single provider | High | Y | 2025-08-20 | audit; access; encryption | SOC 2 (if available) | Auth uptime; backup success | N | 2026-05-31 | RLS review; backup restore test
Stripe | Payments | Y | Finance | Payment/PII | EU/US | Y | n/a | Critical revenue dependency | High | Y | 2025-10-05 | audit; termination; PCI | PCI DSS | Chargebacks; incidents | Y | 2026-04-30 | Portal / webhook monitoring
Atlassian | Jira/Confluence | N | IT | Other | EU | N | n/a |  | Medium | Y | 2024-11-01 | audit; access | ISO 27001 | Ticket SLA | N | 2026-01-15 | Review access rights quarterly
CrowdStrike | EDR | Y | Security | Other | EU | N | n/a |  | High | Y | 2025-03-01 | audit; incident notification | SOC 2 | Detections; coverage | N | 2026-03-01 | Test incident response integration
ServiceNow | ITSM | N | IT | Other | EU | N | n/a |  | Low | Y | 2024-05-20 | audit; termination | ISO 27001 | Backlog; MTTR | N | 2026-02-15 | Consider criticality reassessment
Proofpoint | Email Security | Y | Security | PII/Other | EU | N | n/a |  | Medium | Y | 2025-04-10 | audit; access; MFA | SOC 2 | Phishing rate | N | 2026-04-01 | Add exit plan checklist

## Reporting Timelines
Framework | Initial notification | Intermediate | Final | Source
DORA | ≤4h after classification as major AND ≤24h from detection | ≤72h from classification | ≤1 month from classification | EC Impl. Reg. (EU) 2025/302
NIS2 | Early warning ≤24h of awareness | Incident notification ≤72h; intermediate on request | ≤1 month after notification; progress report if ongoing | NIS2 Art. 23; ENISA guidance (2025)

## Dashboard
Metric | Value | Notes | Unnamed: 3 | Unnamed: 4
Total controls | 136
Compliant (C) | 35
In Progress (IP) | 76
Risk (R) | 25
% Compliant | 25.74%
% In Progress | 55.88%
% Risk | 18.38%
Domain | Compliant | In Progress | Risk | Total
Governance & BoD | 10 | 5 | 0 | 15
ICT RMF | 8 | 13 | 4 | 25
Business Continuity | 5 | 7 | 3 | 15
Incident Mgmt & Reporting | 2 | 14 | 7 | 23
Testing | 2 | 6 | 2 | 10
TPRM | 1 | 13 | 6 | 20
Information Sharing | 2 | 3 | 1 | 6
NIS2 Obligations | 2 | 11 | 2 | 15
EBA Guidelines | 3 | 4 | 0 | 7